THE REPUBLIC OF ALBANIA

THE SCHOOL OF MAGISTRATES

SECTOR OF FINANCE

No.______prot.                                      			Tiranë, on___.___.2024

Subject: 	Report on the economic – financial activity of the School of Magistrates for 2023

TO THE STEERING COUNCIL

OF THE SCHOOL OF MAGISTRATES

Tiranë

For 2023, the activity of the School of Magistrates is financed by three main sources:

- State budget;

- Secondary incomes;

- Support from donors.

- Funding from the state budget

In the application of law no. 84/2022, on the budget of the year 2023, of directive no. 9, date 20.7.2018, on the standard procedures of the implementation of the budget, additional directive of the minister of Finances and Economy no. 2, date 19.1.2023, on the implementation of the budget of the year 2023, the amount of the budget given for the School of Magistrates for the period January – December 2023, is in total 461.639.120 lekë, detailed as follows:

111.673.000 lekë	 for the salaries of full – time and part – time employees;

9.660.000 lekë	 for social/health security;

50.716.000 lekë	 for operational costs (including 2.000.000 lekë incomes);     280.590.120 lekë	 for scholarships (including a special fund 186.120 lekë);

9.000.000 lekë 	 for investments (purchase of different equipments).

Percentage of these units in report to the total amount for the year 2023 is as follows:

| In percentage | % |
| --- | --- |
| (600+601) Salaries and security | 27% |
| (606) Scholarships | 61% |
| (602) Operational costs | 11% |
| (231) Investments | 1% |

The realization of the state budget for the period January – December 2023 is as follows:

1/a. For the unit of budget (600) “Work Salaries” are spent 111.663.079 lekë or 100% of the budget planned for the salaries of servants approved in the organic and of part time servants (experts and part – time lecturers).

1/b. For the unit of budget (601) “Social security” are spent in total 9.360.825 lekë or 97%  of the amount planned for this unit.

2/a. For the unit (602) “Operational costs” are spent in total  50.678.550 lekë or 100% of planned total costs, where are included general office expenses, transport costs, oil costs, travel costs, for transport tickets and diets of the administrative staff, expenses for the consume of electricity, water expenses, as well as phone expenses and different repairs. Also, are included expenses for the heads of practice, members of the evaluation commission for the admission of candidates for magistrate, rewards for the authors of different papers of the journal  “Jeta Juridike” and of other publications of the School, diets of magistrates for the attendance of the Program of Continuous Formation under the Article 5 of law no. 96/2016, expenses for the drafting of education curricula, travels abroad for the full – time academic staff and candidates for magistrate, etc.

2/b. For the unit of budget  (606) “Scholarships and other payments” are spent in total 280.589.653 lekë or 100%  of costs planned for this unit.

Comment: Here are included expenses done for the payment of scholarships for candidates for magistrate, who have attended the first year January – September 2023; the second year January – September 2023, October – December 2023; the third year of school, for the period July – December 2023, and the first year for the period October – December 2023.

3. In the unit of budget “investments” are spent 8.657.602 lekë or 96%  of the planned unit. The biggest part of this difference is the result of the savings from the procedure of public procurement, that make possible the contracting of supplies based on the lowest offer offered.

Comment: The fund determined for investments according to the budget of the year 2023 was  9.000.000 lekë.

II. Financing from secondary incomes realized in 2023

In the draft-budget of the year 2023, that was composed in August, 2022 was planned a fund of 2.000.000 lekë financing from secondary incomes created by the institution, (incomes from the registration in the admission competition and the sale of publications) based on the joint directive no. 672 prot., date 26.12.2006, between the Ministry of Finances and the School of Magistrates.

This directive foresees that the secondary incomes created by the institution, as incomes created from the fee of the registration of candidates for magistrate, 90% of which are used to cover the expenses of their direct cost (in the unit of operations and current costs) and 10% of them are deposited in the state budget, while the incomes realized from the sale of journal, 70% is deposited in the budget and  30% are used to cover the expenses for the journal “Jeta juridike.”

For the year 2023 the secondary incomes from the fee of the registration of candidates for magistrate were in the amount of 5.546.330 lekë and 36% of them was used for the covering of the costs of the development of the admission test, the rest was deposited in the state budget, because was over the amount foreseen in the budget 2.000.000 lekë.

From the sale of publications were realized incomes in the amount of 240.750 lekë. These incomes were not used because expenses for the publication of the journal “Jeta Juridike”, were covered with the funds of the budget planned as above mentioned.

We explain that these incomes cannot be used for other objectives, because they are destined to cover the costs of the expenses for which were created.

The realization of the state budget for the period January – December 2023 in the amount of  99,85%  summarized in the following table:

| Nomination of accounts | Plan | Fact | Difference | % of realization |
| --- | --- | --- | --- | --- |
| 600 Salary | 111.673.000 | 111.663.079 | 9.921 | 100 |
| 601 Security | 9.660.000 | 9.360.825 | 299.175 | 97 |
| 602 Operational costs | 50.716.000 | 50.678.550 | 37.450 | 100 |
| 606 Scholarships and other payments | 280.590,120 | 280.589.653 | 467 | 100 |
| 231 Investments | 9,000,000 | 8.657.602 | 342.398 | 96 |
| Total | 461.639.120 | 460.949.709 | 689.411 | 99,85 |

III. Financial support from international partners of the School for the year 2023

Here is the state of donations that are in our account in the branch of treasury, for the year 2023, as it follows.

| Donors | Inherited in years | Financed year 2023 | Spent year 2023 |
| --- | --- | --- | --- |
| Eipa | 48.915 | 0 | 0 |
| British Embassy | 20.000 | 0 | 0 |
| UNDP | 94.000 | 0 | 0 |
| British College | 6.895 | 0 | 0 |
| Total | 169.810 | 0 | 0 |

During the year 2023 there were no incomes from donations in monetary amounts, but there were some sponsorship of training activities of the calendar of continuous formation.

As above mentioned, the funds of donors remained in years are inheritable for the year 2024.

DIRECTOR

ARBEN RAKIPI

Conceived  by: E. Qokaj, A. Havari

Edited by : A. Haruni

No. of copies: 2 (two)

Date  23.1.2024

FINANCIAL SOURCES IN YEARS

| Years | State budget (lekë) | Contributions from donors (lekë) |
| --- | --- | --- |
| 1997 | 16800000 | 0 |
| 1998 | 24778000 | 17736000 |
| 1999 | 25000000 | 23540000 |
| 2000 | 32834000 | 24536000 |
| 2001 | 29471000 | 2595000 |
| 2002 | 33578000 | 1222000 |
| 2003 | 48568000 | 703000 |
| 2004 | 58550000 | 6751000 |
| 2005 | 67000000 | 4129000 |
| 2006 | 53000000 | 1640000 |
| 2007 | 53000000 | 2817000 |
| 2008 | 52750000 | 3814000 |
| 2009 | 56900000 | 3000000 |
| 2010 | 52700000 | 3000000 |
| 2011 | 55000000 | 8070943 |
| 2012 | 55594000 | 5025726 |
| 2013 | 56100000 | 3938000 |
| 2014 | 59724000 | 0 |
| 2015 | 60500000 | 0 |
| 2016 | 70000000 | 1106300 |
| 2017 | 91000000 | 4453915 |
| 2018 | 121000000 | 0 |
| 2019 | 178805000 | 1869763 |
| 2020 | 190150000 | 3849300 |
| 2021 | 254050000 | 2534700 |
| 2022 | 298654270 | 224990 |
| 2023 | 461639120 | 0 |